## Sheet1
FlyAway Agile Project Plan
Task Name | Priority | Owner | Start Date | End Date | Status
Sprint #1: Analysis and Design
Making Sprint Plan | High | sai purandhara | 2022-07-14 | 2022-04-17 | Done
Specification document | Low | sai purandhara | 2022-07-15 | 2022-04-18 | Done
Prepare Algorithm | High | sai purandhara | 2022-07-16 | 2022-04-18 | Done
Create Flow Chart | Medium | sai purandhara | 2022-07-17 | 2022-04-18 | Done
Setup Git Repository | High | sai purandhara | 2022-07-18 | 2022-04-18 | Done
Sprint #2: Develop and Execute
Setup Environment | Medium | sai purandhara | 2022-07-19 | 2022-05-01 | Done
Code css | High | sai purandhara | 2022-07-19 | 2022-05-01 | Done
Code typescript | High | sai purandhara | 2022-07-19 | 2022-05-01 | Done
Code for html | High | sai purandhara | 2022-07-19 | 2022-05-01 | Done
Code to Navigate and close Application | Medium | sai purandhara | 2022-07-20 | 2022-05-01 | Done
Sprint #3: Test, Fix & Install
Test the Application | High | sai purandhara | 2022-07-21 | 2022-05-01 | Done
Fix issues | High | sai purandhara | 2022-07-21 | 2022-05-01 | Done
Regression Test | Low | sai purandhara | 2022-07-21 | 2022-05-01 | Done
Upload to Git Repository | Medium | sai purandhara | 2022-07-21 | 2022-05-02 | Done
Submit Project | High | sai purandhara | 2022-07-21 | 2022-05-02 | Done